## Sheet1
| Task | Responsible Unit | Status | Comment
1 | First team meeting "Who is Who" | all | done
2 | Create a GitHub repository | petra | done | https://github.com/janito84/naturalmilk
3 | Create a GitHub acconts | all | done
4 | Research for an existing application which can be use in the project | boyko | done
5 | Discuss task in the project | all | done
6 | Research for best SRS templates or examples | all | done | added some interesting SRS documents
7 | Research for best Use cases templates or examples | all | done | added some interesting SRS documents
8 | Research for best Test scenarios templates or examples | all | done | added some interesting SRS documents
9 | Research for best way to implement automation tests with Selenium IDE | boyko | done
10 | Write a SRS document about selected application. | all | done
11 | Write a Use cases for application functionality | janito, dessi | done
12 | Write a Testplan for functionality test. | all | done
13 | Write test cases | petra | done
14 | Create some automation tests using Selenium IDE | boyko | done
15 | Shaping the final version for SRS | ptra, dessi | done
16 | Shaping the final version for Test plan | janito | done
17 | Design and write a presentation of the project using slides, screens, mock-ups and etc. | petra | done
19 | Test and add bug | janito, boyko | done
20 | Preparing all documents and apllication for presentation.
21 | Preliminary presentation of the project
22 | Final Presentation of the project